## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Inconsistent dataset formatting causing incorrect preprocessing | Sprint 1 |  | Data Defect | Cleaned dataset, handled null values, standardized text | Sprint 1 – Day 2 | Closed | Improved model input quality
|  |  | Low classification accuracy during initial training | Sprint 1 |  | Model Defect | Applied better preprocessing and hyperparameter tuning | Sprint 1 – Day 4 | Closed | Accuracy improved after tuning
|  |  | Priority prediction accuracy significantly lower | Sprint 1 |  | Model Defect | Reworked label encoding and adjusted model parameters | Sprint 1 – Day 9 | Closed | Balanced class distribution handled
|  |  | Model not loading in Flask backend | Sprint 2 |  | Integration Defect | Corrected file path handling and loaded model at startup | Sprint 2 – Day 6 | Closed | Reduced runtime errors
|  |  | Login validation failing for valid users | Sprint 2 |  | Backend Defect | Fixed DB schema mapping and authentication query | Sprint 2 – Day 3 | Closed | Proper credential validation implemented
|  |  | Duplicate Ticket ID generation | Sprint 2 |  | Database Defect | Implemented unique ID logic using auto-increment/UUID | Sprint 2 – Day 10 | Closed | Ensured ticket uniqueness
|  |  | Ticket assignment not reflecting in team dashboard | Sprint 3 |  | Logic Defect | Fixed assignment logic and corrected filtering query | Sprint 3 – Day 7 | Closed | Dashboard updated correctly
|  |  | Admin able to update ticket status (role violation) | Sprint 3 |  | Access Control Defect | Added backend-level restriction validation | Sprint 3 – Day 11 | Closed | Enforced strict role hierarchy
|  |  | Team members viewing tickets outside assigned team | Sprint 3 |  | Security Defect | Implemented team ID-based filtering | Sprint 3 – Day 13 | Closed | Access properly restricted
|  |  | Redirect loop after implementing hybrid routing | Sprint 4 |  | Routing Defect | Corrected login-state condition handling | Sprint 4 – Day 6 | Closed | Stable routing achieved
|  |  | UI inconsistency across public pages | Sprint 4 |  | UI Defect | Refactored base template and unified styling | Sprint 4 – Day 3 | Closed | Improved visual consistency
|  |  | Deployment CLI command not recognized | Sprint 4 |  | Deployment Defect | Installed necessary tools and configured PATH | Sprint 4 – Day 12 | Closed | Deployment environment stabilized

## Sheet2
Logical
User Interface
Maintainability
Standards
Others